## Final Blank template 3 yr plan
A FRAMEWORK FOR FRENCH AS A SECOND LANGUAGE, KINDERGARTEN TO GRADE 12
"Students in English-language school boards have the confidence and ability to use French effectively in their daily lives."
3-YEAR PLAN
DUE DECEMBER 13, 2013
Name of Board: Avon Maitland District School Board
FSL Contact: Jane Morris | Title: Superintendent of Education | Telephone: 519 527 0111 x116 | Email: jane.morris@ed.amdsb.ca
FSL PROVINCIAL GOAL 1: INCREASE STUDENT CONFIDENCE, PROFICIENCY, AND ACHIEVEMENT IN FSL
Planned Progress to Achieve Goal(s)
District School Board Baseline Data (Areas of Greatest Need) | District School Board Goal(s) |  | Year 1 (2014-15) | Year 2 (2015-16) | Year 3 (2016-17)
The mark distribution in the oral strand of grade 4 Core French on the June 2013 report card indicate a small range of marks (63% - 70% across the board). This range, as compared to other subjects, highlights a need to establish valid and reliable student achievement baseline data and ensure that subsequent student achievement data collected is valid and reliable. | To establish valid and reliable baseline student achievement data in the strand of oral communication in grade 4 Core French in 2014 and improve on this baseline each subsequent year.
|  |  | baseline data | 2% | 2%
To align assessment and evaluation practices in FSL with Growing Success, the AMDSB Assessment, Evaluation and Reporting document and the revised FSL curriculum.
District School Board Goal(s) | Planned Actions and Target Audiences
| Year 1: 2014-2015 | Year 2: 2015-2016 | Year 3: 2016-2017
To establish valid and reliable student achievement baseline data in the strand of oral communication speaking in grade 4 Core French. | Elementary Core grade 4 French teachers will develop and administer a common criterion-referenced oral speaking assessment task to all Core FSL grade 4 students. Moderated marking with co-constructed success criteria of this common assessment will result in the establishment of valid and reliable student achievement baseline data for in the strand of grade 4 oral communication speaking. | The grade 4 oral speaking common assessment will be administered to grade 4 core students and compared to year 1 scores. | The grade 4 speaking common assessment will be administered to grade 4 students and compared to year 1 and year 2 scores. The grade 5 speaking common assessment will be administered to grade 4 students and compared to year 2 scores.
|  | Core FSL elementary teachers will develop and administer a common criterion-referenced speaking assessment to all Core FSL grade 5 students. Moderated marking with co-constructed success criteria of this common assessment will result in the establishment of valid and reliable student achievement baseline data in the strand of grade 5 oral communication. speaking. Results will be compared to year 1 data from same cohort. | Core FSL elementary teachers will develop and administer a common criterion-referenced speaking assessment to all Core FSL grade 6 students. Moderated marking with co-constructed success criteria of this common assessment will result in the establishment of valid and reliable student achievement baseline data in the strand of grade 6 oral communication speaking. Results will be compared to year 1 and year 2 data from the same cohort. This is currently happening in our Regional PLC groups. We have also added and collaborated on the Component #2 of the CEFR Continuum: Learning, teachering and assesement have a proficiency angle and are trying to use that to inform our teaching strategies within our tasks.
To align assessment and evaluation practices in FSL with Growing Success, the AMDSB Assessment, Evaluation and Reporting document and the revised FSL curriculum, CEFR, FSL for All, FSL Framework and the ELL document | Establish baseline data from FSL teacher perceptual data regarding their understanding and implementation of assessment as, for and of learning practices to inform and support the inquiries in our regionally based FSL PLCs. | Continue to support regionally based PLC inquiries related to areas outlined on the teacher survey. | Continue to support regionally based PLC inquiries related to areas outlined on the teacher survey. This PLCs are very well attended with 4 1/2 day release times per teacher. Some of the highlights from our debrief last year include: - clearer perspective on students who work at level 2 - better curriculum connections with the CEFR - better assessment tools and co-constructed rubrics - more collaboration with colleagues including moderation
FSL PROVINCIAL GOAL 2: INCREASE THE PERCENTAGE OF STUDENTS STUDYING FSL UNTIL GRADUATION
District School Board Baseline Data (Areas of Greatest Need) | District School Board Goal(s) |  | Year 1 (2014-15) | Year 2 (2015-16) | Year 3 (2016-17)
The 2013 attrition rate from grade 9 - grade 10 Core French is 81%. | To explore strategies to reduce the attrition rate from grade 9 to grade 10 Core French from 81% in 2013 to 74% by June 2017. |  | -2% (81%) | -2% (71%) | -3% (75%, however, a -6% decrease overall)
District School Board Goal(s) | Planned Actions and Target Audiences
| Year 1: 2014-2015 | Year 2: 2015-2016 | Year 3: 2016-2017
Decrease the attrition rate from grade 9 to grade 10 Core French from 81% to 74% by June 2017. | Develop and promote an e-learning FSF2D course. | Promote the on-line FSF2D course. | Monitor enrollment and credit accumulation in the on -line FSF2D course . Did not need to offer this course as every Secondary school in AMDSB has a FSF2D course being offered this school year. However, we saw a need in FSF3U/4U, therefore this summer we are offering a Summer French Credit Course travelling to Quebec City, Montreal and Halifax.
| To develop and administer a student survey for grade 9 FSL students pinpointing the reasons for including or excluding French from their grade 10 course selection. | To investigate and address or build on some of the areas outlined from the student survey results. | Administer student survey to current grade 9, grade 10 and 11 students pinpointing reasons for including or excluding French from their grade 10, 11 or 12 course selections. This will occur in April-May 2017
| To emphasize, with grade 9 students, the shift towards authentic, action oriented, functional Core French studies in secondary school through secondary FSL teachers, guidance departments, and information sharing sessions during course selection. | Administer student survey to current grade 9 and 10 Core FSL students pinpointing reasons for including or excluding French from their grade 10 or grade 11 course selections. | To promote the continuation of FSL studies after grade 9 with a focus on oral based, functional French studies through secondary teachers, principals, guidance and information sessions.
Implementation of a blended FSF 4U course with 3 secondary schools and 19 students beginning February 2015.
| Offer immersion excursion activities/trip to students in FSL courses in grades 7, 8 & 9s in grade 10 Core French language courses. | To promote the continuation of FSL studies after grade 9 with a focus on authentic, action-oriented, functional French studies through secondary teachers, guidance and information sessions. 25 students from AMDSB were selected and participated in a 5-day French excursion to St. Donat, Quebec. | To investigate and address or build on some of the areas outlined from the student survey results. 50 students were selected and will particpate in February 2017 in a 5-day French excursion to St. Donat, Quebec.
FSL PROVINCIAL GOAL 3: INCREASE STUDENT, EDUCATOR, PARENT, AND COMMUNITY ENGAGEMENT
District School Board Baseline Data (Areas of Greatest Need) | District School Board Goal(s) |  | Year 1 (2014-15) | Year 2 (2015-16) | Year 3 (2016-17)
30 % of secondary French Immersion students and grade 12 Core FSL students in AMDSB challenged the DELF in Spring 2013 | To increase the number of students challenging the DELF in AMDSB from 30% in Spring 2013 to 37% by June 2017. |  | 2% - 78 challenged | 2% - 104 challenged: 48% of Grade 12 core students challenged the DELF | 3%
| To increase the number of schools having students challenge the DELF from 4 in Spring 2013 to 7 by June 2017. |  |  | All of AMDSB's Secondary schools participated.
District School Board Goal(s) | Planned Actions and Target Audiences
| Year 1: 2014-2015 | Year 2: 2015-2016 | Year 3: 2016-2017
To increase the number of students challenging the DELF in AMDSB from 30% in Spring 2013 to 37% by Spring 2017. | Raise the profile and interest of DELF in AMDSB through the development of an information brochure to distribute to all secondary French Immersion and grade 12 Core FSL students. | Update information on brochure. Continue to distribute to secondary French Immersion students and grade 12 Core FSL students. | Update information on brochure. Continue to distribute to secondary French Immersion students and grade 12 Core FSL students. Will update this again this year to show progress of DELF participants.
| Develop and maintain a current web presence on our board website regarding DELF successes and information. | Update and maintain a current web presence on our board website regarding DELF successes and information. | Update and maintain a current web presence on our board website regarding DELF successes and information. This included on Facebook, Twitter and the Board website.
To increase the number of schools having students challenge the DELF from 4 in Spring 2013 to 7 in Spring 2017. | Promote and support correcteur training with FSL teachers to develop an awareness of and the benefits of the DELF. | Continue to promote and support correcteur training with FSL teachers to develop an awareness of and the benefits of the DELF. | Continue to promote and support correcteur training with FSL teachers to develop an awareness of and the benefits of the DELF.
| Train an additional DELF formateur in AMDSB | Lindsay Stewart was trained as a formatricein Ottawa in December 2015. | 4 teachers were trained as Correctrices in the Summer of 2016. AMDSB now has a total of 30 Correctrices.
Notes:
Annual dialogues with ministry staff, and a progress report to be submitted in 2016-2017, will focus on outcomes of actions and progress toward meeting school board goals for FSL.
Although Year 1 of the plan is 2014-15, boards have the flexibility to begin actions in 2013-14.
Sign-off for 3-Year FSL Plan
Approved by: |  | (Superintendent responsible for FSL) Jane Morris | Date: 2013 12 12
Approved by: |  | (Director of Education) Ted Doherty | Date: 2013 12 12
Note on A11: Laurie Long: speaking
Note on B11: Laurie Long: speakng
Note on B23: Laurie Long: Grade 4 Task - criterion based task All grade 4 teachers will administer this task at then end of the year (to support FSL Framework goal #1) Example: introduce family members to teacher at a school event Expect students to: a) greet teacher b) introduce each family member by role and name c) introduce teacher to family members d) close introduction with a comment/statement that leads to the next event Learning goal for this task We are learning to… Introduce our family members to our teacher in French. Success Criteria I know I am successful when I can use… • simple sentences • the first person consistently (je, mon, ma, mes) • the present tense consistently • accurate pronunciation for familiar words • gestures appropriate for the purpose and audience (point, smile, nod) • familiar words (presente) accurately to greet my teacher, (bonjour) introduce my family members (mere, pere, soeur)and close the introduction …to make my information understood in French. • Based on the CEFR this task would fall in the early stages of A1: (simple, mainly isolated, phases and sentences, basic words)
Note on C24: Laurie Long: speaking
Note on D24: Laurie Long: spekaing
Note on B25: Laurie Long: Results from Teacher Survey - June 2014 French Teacher Survey 2013-14 Beginning Developing Integrating Sustaining Awareness of Assessment for Learning 0% 37% 58% 5% Implementation of Assessment for Learning 11% 42% 47% 0% Awareness of Assessment as Learning 0% 32% 63% 5% Implementation of Assessment as Learning 16% 26% 47% 11% Awareness of Assessment of Learning 0% 11% 58% 32% Implementation of Assessment of Learning 5% 16% 47% 32%
Note on A43: Laurie Long: Attrition Rates School Enroll Gr. 9 Gr 10 Gr. 10 Gr. 11 2012 - 13 13 - 14 Retention Attrition 2012-2013 13 - 14 CHSS 125 30 24% 86% 20 8 40% GDCI 101 39 39% 61% 30 11 37% LDSS 139 30 22% 78% 53 35 66% MDHS 61 0 0% 100% 10 0 0% SHDS 102 18 18% 82% 20 10 50% DCVI 83 30 36% 64% 18 11 61% SCSS 148 21 14% 86% 23 11 48% SNSS 160 24 15% 85% 21 10 48% FEMADILL 133 13 9% 91% 31 12 39% TOTAL 1052 205 19% 81% 226 108 47%
Note on B43: Laurie Long: with the revised currculum, plans are to develop this course in summer 2015
Note on B44: Laurie Long: Number of Participants 210 French in Gr10 No Yes Academic 59% 41% Applied 96% 4% Grand Total 69% 31% I like French Never Sometimes Most of the time Academic 21% 29% 50% Applied 28% 54% 19% Grand Total 23% 36% 42% I do my best on French activities in class. Never Sometimes Most of the time Academic 8% 28% 64% Applied 6% 36% 58% Grand Total 7% 30% 62% Does not fit my timetable No Yes Academic 74% 26% Applied 81% 19% Grand Total 77% 23% I don't need French for the future No Yes Academic 70% 30% Applied 56% 44% Grand Total 65% 35% Because I don't have to No Yes Academic 65% 35% Applied 50% 50% Grand Total 60% 40% I need French for my future No Yes Academic 52% 48% Applied 100% 0% Grand Total 54% 46% I am interested in French No Yes Academic 36% 64% Applied 0% 100% Grand Total 35% 65%
Note on B45: Laurie Long: - system memo to all administrators and secondary FSL teachers and guidance re: Ontario Schools p. 55 (re FSL additonal compulsory credits) - transition forms (grade 8 - 9) have been updated removing French as the default substitution
Note on B52: Laurie Long: # of students challenging the DELF 2014 - 58 students = 47%
Note on B53: Laurie Long: # of schools participating in 2014 = 6
Note on B57: Laurie Long: DELF Brochure created 2014 and updated 2015
Note on B58: Laurie Long: complete in 2014 updated in 2015
Note on B59: Laurie Long: correcteur training provided through CEFR regional August 2014 provided correcteur training at AMDSB October 25 & 26, Nov 1&2